## Objects
ID | Title | Description | Type | Module | Complexity
W-001 | Purchase order approval workflow | Multi-level release strategy for purchase orders above 10k EUR, routed to cost-center owner then procurement lead. | Workflow | MM | Complexe
R-001 | Open items ageing report | ALV ageing report of open customer items with drill-down to FI document and dunning level. | Report | FI | Moyen
I-001 | Bank statement inbound interface | CAMT.053 intraday bank statement import with automatic clearing proposal. | Interface | FI | Tres complexe
C-001 | Customer master conversion | One-time migration of legacy customer masters to S/4 Business Partners with address deduplication. | Conversion | SD | Complexe
E-001 | Delivery due-list enhancement | BAdI enhancement adding credit-block and route checks to the delivery due list. | Enhancement | SD | Moyen
F-001 | Order confirmation form | Adobe Forms order confirmation replacing the legacy SAPscript layout, with brand template. | Form | SD | Simple

## Tickets
Object ID | Ticket ID | Title | Description | Priority | Status
W-001 | W-001-TK-001 | Design release strategy matrix | Workshop with procurement to define release codes and thresholds. | High | New
W-001 | W-001-TK-002 | Implement workflow template | Build the SWDD workflow template and agent determination. | High | New
W-001 | W-001-TK-003 | Configure approval notifications | Email and Fiori My Inbox notifications for pending approvals. | Medium | New
R-001 | R-001-TK-001 | Build ageing ALV report | Core ALV grid with ageing buckets 30/60/90/120. | Medium | New
R-001 | R-001-TK-002 | Add dunning level drill-down | Navigation from ageing line to dunning history. | Low | New
I-001 | I-001-TK-001 | Map CAMT.053 to bank statement | Field mapping and conversion rules for the intraday format. | Critical | New
I-001 | I-001-TK-002 | Automatic clearing proposal | Matching rules on reference and amount for automatic clearing. | High | New
I-001 | I-001-TK-003 | Error handling and reprocessing | Monitor with reprocess action for failed statements. | Medium | New
C-001 | C-001-TK-001 | Extract and cleanse legacy customers | Extraction program with address normalization and dedup keys. | High | New
C-001 | C-001-TK-002 | Load Business Partners | BP load via CVI with role assignment and number-range mapping. | High | New
E-001 | E-001-TK-001 | Implement due-list BAdI | Credit-block and route checks in LE_SHP_DELIVERY_PROC. | Medium | New
F-001 | F-001-TK-001 | Build Adobe form layout | Order confirmation layout with brand header and item table. | Medium | New
F-001 | F-001-TK-002 | Connect print program | Output-management integration and form data provider. | Low | New